***September 2, 2022 – Updated Draft***

**Waskesiu Vision 2028 - Community Action Plan**

**Implementation Strategy**

| **AREA** | **ACTION** | **LEAD** | **PARTNER** |  | **TIMING** | | | | | | |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | **2021** | **2022** | **2023** | **2024** | **2025** | **2026** | **2027** |
| 1. Infrastructure | Establish a parking strategy to address parking congestion/safety issues in portions of the Waskesiu townsite during the summer months (particularly in Bluebird to Pelican) | PCA | WCC/  WSRA |  |  |  |  |  |  |  |
| 1. Infrastructure | Develop a conceptual plan for the main beach/day use areas (i.e., the area near the lake from the Nature Centre to the Community Hall) | PCA | WCC |  |  |  |  |  |  |  |
| 1. Infrastructure | Refurbish the main beach area breakwater | PCA |  |  |  |  |  |  |  |  |
| 1. Infrastructure | Improve availability/access to sufficient staff accommodation and/or lots for use by the Waskesiu business community and PCA (i.e., for “need to reside” staff) | PCA | Chamber/  WCC | *Completed* |  |  |  |  |  |  |
| 1. Infrastructure | Develop a revitalization plan for the Paul Horne Arena (to improve the facility and to also facilitate year-round activities) | WRA | Foundation/PCA |  |  |  |  |  |  |  |
| 1. Infrastructure | Revitalize the Paul Horne Arena (to improve the facility and to also facilitate year-round activities) | WRA/PCA | Foundation |  |  |  |  |  |  |  |
| 1. Infrastructure | Implement the “Trail Plan Prince Albert National Park 2018 -2022” to improve the Waskesiu trail network | PCA |  |  |  |  |  |  |  |  |
| 1. Infrastructure | Develop a plan for an off-leash dog park for Waskesiu | PCA | Foundation  /WRA |  |  |  |  |  |  |  |
| 1. Infrastructure | Construct an off-leash dog park in Waskesiu | PCA | WRA/  Foundation |  |  |  |  |  |  |  |
| 1. Infrastructure | Plan/design a skateboard park | TBD | TBD |  |  |  |  |  |  |  |
| 1. Infrastructure | Replace the public washrooms at the Main Beach | PCA |  | *Completed* |  |  |  |  |  |  |
| 1. Infrastructure | Install a dock at the Crean Lake Day Use Area | PCA | Foundation | *Completed* |  |  |  |  |  |  |
| 1. Infrastructure | Replace the public washrooms located near the Community Hall | PCA |  |  |  |  |  |  |  |  |
| 1. Infrastructure | Undertake storm drain improvements at, or affecting, the 4-way stop intersection (as needed) | PCA |  |  |  |  |  |  |  |  |
| 1. Infrastructure | Replace all fish cleaning buildings in the Park (5) | PCA |  |  |  |  |  |  |  |  |
| 1. Infrastructure | Complete an assessment of the Recreation Centre Building (regarding building settling/foundation issues) | PCA |  |  |  |  |  |  |  |  |
| 1. Infrastructure | Develop a plan to refurbish the interior of the Recreation Centre building | WRA/  Foundation | PCA |  |  |  |  |  |  |  |
| 1. Infrastructure | Refurbish the interior of the Recreation Centre Building | WRA/  Foundation | PCA |  |  |  |  |  |  |  |
| 1. Infrastructure | Golf Course Pro Shop renovation | PCA | WGC |  |  |  |  |  |  |  |
| 1. Infrastructure | Complete Spruce Ridge Trailer Park expansion (at the far end of Montreal Drive near the Library/Recreation Hall) | PCA |  | *Completed* |  |  |  |  |  |  |
| 1. Infrastructure | Undertake a “Phase I” Water and Sewer Line Assessment | PCA |  | *Completed*  *Completed* |  |  |  |  |  |  |
| 1. Infrastructure | Install Electric Vehicle Charging stations in the townsite | PCA |  |  |  |  |  |  |  |  |
| 1. Infrastructure | Renovation of Golf Course Administration Office and Washrooms | WGC | PCA |  |  |  |  |  |  |  |
| 1. Infrastructure | Construct new Golf Course Maintenance Building | WGC | PCA |  |  |  |  |  |  |  |
| 1. Infrastructure | Refurbish the existing pathway/trail between Kapasiwin and Waskesiu Drive | WSRA? | Foundation  PCA? |  |  |  |  |  |  |  |
| 1. Infrastructure | Investigate the potential installation of “deep water” infrastructure to service residential cabins/cottages in Waskesiu | WSRA | WCC |  |  |  |  |  |  |  |
| 1. Infrastructure | Design and develop a connecting pathway and related areas between Lakeview Drive and Waskesiu Drive | Foundation | PCA |  |  |  |  |  |  |  |
| 1. Infrastructure | Investigate the construction of additional camp kitchens in the Waskesiu townsite and at outlying beaches/lakes | Foundation | PCA |  |  |  |  |  |  |  |
| 1. Infrastructure | Investigate the potential construction of, or the acquisition of, a large community stage (permanent or mobile/collapsible) | WCC | Foundation/WRA? |  |  |  |  |  |  |  |
| 1. Infrastructure | Explore the feasibility of a trail connecting Waskesiu and Elk Ridge | Foundation/PCA | Elk Ridge |  |  |  |  |  |  |  |
| 1. Image | Continue Waskesiu townsite centre beautification & revitalization program (e.g., flowers, signage, weed control, clean-up) | Chamber | Foundation/ WCC/ Museum/ PCA |  |  |  |  |  |  |  |
| 1. Image | Improve and develop additional thematic and informational signage, heritage/cultural identifiers | PCA | Museum/  Foundation |  |  |  |  |  |  |  |
| 1. Recreation and Amenities | Complete the environmental remediation (capping) of the existing lawn bowling area for future use as outlined in the approved Recreation Area “Master Plan” | PCA |  | *Completed* |  |  |  |  |  |  |
| 1. Recreation and Amenities | Complete a new multi-use sport court, upgraded pathways, picnic shelter, shuffleboard area, children’s ninja line, FireSmart tree removal, and initial landscaping (as contemplated in the Recreation Area “Master Plan”) | WRA | Foundation  /PCA |  | *Completed* |  |  |  |  |  |
| 1. Recreation and Amenities | Complete the balance of the “Waskesiu Recreation Area Renewal” work contemplated in the Recreation Area “Master Plan” (i.e., revitalized lawn bowling area, new benches, outdoor foosball & ping pong tables, remaining landscaping) | WRA | Foundation |  |  |  |  |  |  |  |
| 1. Recreation and Amenities | Install a beach volleyball area near the refurbished lawn bowling area | WRA/  Foundation |  |  |  |  |  |  |  |  |
| 1. Recreation and Amenities | Refinish the oak floors in both the Waskesiu Community Hall & Terrace Gardens Hall (to ensure hall flooring is maintained to a high standard) | Chamber | PCA |  |  |  |  |  |  |  |
| 1. Recreation and Amenities | Work to ensure the Community Hall bat problem is resolved | Chamber | PCA |  |  |  |  |  |  |  |
| 1. Recreation and Amenities | Promote existing (and create additional) winter activities within the Waskesiu townsite (e.g., ice fishing shacks, cross country ski trail maintenance, outdoor ice-skating surface, Winter Festival, etc.) | Chamber | PCA/WCC/  WRA |  |  |  |  |  |  |  |
| 1. Recreation and Amenities | Determine the feasibility of a “Waskesiu Community Garden” | TBD | TBD |  |  |  |  |  |  |  |
| 1. Recreation and Amenities | Assess options to install playground equipment in the townsite including potentially replacing the accessible toddler playground on the main beach | Foundation | PCA |  |  |  |  |  |  |  |
| 1. Visitation | Improve messaging, information, and delivery systems and capability; improve overall communications capability and systems for key stakeholders and for PCA | WCC | PCA/ WSRA/ Chamber |  |  |  |  |  |  |  |
| 1. Visitation | Work with key stakeholder groups and other agencies to promote Waskesiu as a preferred resort/business conference destination; help to enhance support for (and awareness of) events | Chamber | PCA/WCC/  WRA |  |  |  |  |  |  |  |
| 1. Visitation | Develop a strategy to attract/plan more annual events (including recurring conferences and festivals) year-round | Chamber | WCC/  WRA |  |  |  |  |  |  |  |
| 1. Community Life | Create a “Waskesiu Volunteer Committee” and a Volunteer Action Plan | WRA | WSRA/  PCA/WCC |  |  |  |  |  |  |  |
| 1. Community   Life | Develop Waskesiu’s 100 Year Anniversary Celebration Plan | PCA/  WCC | Chamber/  WRA/WSRA/  Foundation  Museum/  WGC? |  |  |  |  |  |  |  |
| 1. Community Life | Implement a community-wide “Waskesiu Legacy” planned giving program | Foundation | WRA/ WGC  Museum |  |  |  |  |  |  |  |
| 1. Community Life | Identify additional “Memorial” options in the townsite or the Park (e.g., more benches, memorial forest/model forest, donor wall, brick or masonry stone walking path, additional camp kitchens) | Foundation | PCA/  WRA |  |  |  |  |  |  |  |
| 1. Community Life | Design and develop a physical (or a virtual) Waskesiu Community Builder/Volunteer/Pioneer Recognition/History project | Museum | WSRA |  |  |  |  |  |  |  |
| 1. Natural Environment | Implement the 2019 Vegetation Management Strategy in the Waskesiu townsite | PCA | WCC/ WGC |  |  |  |  |  |  |  |
| 1. Natural Environment | Develop a comprehensive strategy regarding waste management in the Waskesiu townsite including for composting/recycling | PCA |  |  |  |  |  |  |  |  |
| 1. Community Planning, Policy and Practice | Work collaboratively to improve and modernize Parks Canada’s planning and development processes (including the Cottage Regulations) | WCC | WSRA/  Chamber/  PCA |  |  |  |  |  |  |  |
| 1. Community Planning, Policy and Practice | Review (and amend as necessary) the existing Waskesiu Land Use Directive | PCA | Chamber/  WCC/  WSRA |  |  |  |  |  |  |  |
| 1. Community Planning, Policy and Practice | Develop a Waskesiu Townsite Built Heritage Policy/Protocol | TBD | Museum |  |  |  |  |  |  |  |
| 1. Reconciliation | Undertake initiatives in Waskesiu that are designed to:  a. help improve participation of Indigenous people in the Waskesiu Vision 2028 (and beyond) strategic planning process;  b. help build and enhance relationships between Indigenous & non-Indigenous people (by increasing learning opportunities, understanding, and awareness) | WCC/  PCA | Foundation  /Museum |  |  |  |  |  |  |  |